REPUBLIQUE DU CAMEROUN

*****

Paix-Travail-Patrie

REPUBLIC OF CAMEROUN

*****

Peace-Work-Fatherland

AFRILAND FIRST BANK

Directions des Systèmes d’Information

Design and Implementation of a Software Development Automation Platform

Plan of Work

Presented by:

FORBIN Astera-Lainey Etonde

and

KOUETCHE SIMO Yann Jefferson

Engineering students in Computer Science and Information Systems

Academic Year 2025-2026

June 2026

Based on the User Stories backlog (338 Story Points, 8 sprints).
Prepared on: 17 June 2026

## Project Schedule

| Sprint | Objective | Start Date | End Date | Services Required | Key Deliverables |
| --- | --- | --- | --- | --- | --- |
| 1 | User Management & Authentication | 15 June 2026 | 21 June 2026 | Authentication Service, API Gateway | User registration, login, password reset, logout, JWT security layer, error-handling framework, dashboard scaffold. |
| 2 | Project Lifecycle Management | 22 June 2026 | 28 June 2026 | API Gateway, Project Service, AI orchestrator service. | Project creation with document upload and guided questions, project listing, search, deletion, file parsing pipeline (PDF/DOCX), project workspace routing. |
| 3 | Requirements Extraction & Validation | 29 June 2026 | 05 July 2026 | API Gateway, Requirement Service, RAG service, AI orchestrator service. | Automatic requirements generation, requirements review workspace, approval with RAG initialization, change request workflow, iterative regeneration. |
| 4 | UML Diagram Generation & Approval | 06 July 2026 | 12 July 2026 | UML Service, API Gateway, RAG service, AI orchestrator service, Kroki(external), Version service | PlantUML generation, Kroki rendering integration, design review workspace, approval workflow, diagram regeneration and versioning. |
| 5 | System Documentation Generation | 13 July 2026 | 19 July 2026 | Document Service, API Gateway, RAG service, AI orchestrator service, Version service | Documentation generation, RAG indexing, validation, regeneration workflow, DOCX export. |
| 6 | Code Generation & Version Management | 20 July 2026 | 26 July 2026 | API Gateway, Code Service, RAG service, AI orchestrator service, Version service | Full code generation, automatic validation/self-correction, code approval, version snapshots, ZIP download. |
| 7 | Deployment Packaging & Version Timeline | 27 July 2026 | 02 Aug 2026 | API Gateway, Deployment Service, AI orchestrator service, Version service | Docker deployment package generation, deployment ZIP download, version timeline, historical download, restoration. |
| 8 | Dockerise and final Presentation | 03 Aug 2026 | 09 Aug 2026 | / | Dockerised application, deployment documentation, validation report, final presentation, and deployment-ready package for the company's server. |

## NB: Testing is done throughout each sprint!

## Milestones

M1. Authentication and security completed

M2. Project management workflow operational

M3. Requirements generation validated

M4. Diagram generation approved

M5. Documentation generation completed

M6. Code generation and validation completed

M7. Deployment package available

M8. Final testing and hardening completed